# Menu

# Important Times/Dates:

- Recurring weekly :

- Meeting (With Supervisor): Wednesday 12:00 pm ~ 12:45pm

- Meeting (Team only): Tuesday 11:00 am ~ 12:00 pm

- Meeting (With client): Thursday 5:00 pm ~ 6:00pm (Temporary for Jan 22nd)

## Full class meetings (8:30-11:30am, LH4096):

- • January 8th : Introduction to MGTA621

- • January 22nd : Team resumé and team charter (presented by career center)

- • January 29th : Introduction to Project Management

- • February 12th : Midterm internal presentations to MMA faculty panel

o Presentation slides should be submitted to faculty advisor by Feb 10th

- • April 2nd : Final internal presentations to MMA faculty panel

o Presentation slides and draft report should be submitted to faculty advisor by March 31st

## Milestones:

- • Week of January 22nd : Client meeting(Thursday 5:00 pm ~ 6:00 pm (Temporary for Jan 22nd) ), Project kickoff

- • Week of February 23rd -27th : Client meeting, Midterm Presentation

- • Week of April 13th -17th : Client meeting, Final Presentation

## Deadlines:

- • January 12th : Signed NDAs

- • February 10th: Submit Midterm internal presentation slides to faculty advisor

- • February 12th : MMA consulting agreement and statement of work

- • March 31st: Submit Final internal presentation slides to faculty advisor

- • April 17th : Final report

# Duty allocation:

- Project Manager: Amreen, Shuyue

- Contact with client: Jiahua(David)

- Note taking: Shuyue, Amreen,Yue Wang(Nikita)

- Technical: Mohammed